## Capital 2026-27
SCHEDULE OF PROCUREMENT PLANS IN RESPECT OF ADVERTISED COMPETITIVE BIDS FOR THE 2026/2027 FINANCIAL YEAR FOR GOODS, SERVICES AND INFRASTRUCTURE PROJECTS IN EXCESS OF R 300 000 (INCLUDING ALL APPLICABLE TAXES)
Directorate | Tender Description | Project Name |  | Tender Number | IDP Reference | Strategic Objectives | Contract Owner | Contract Manager | Contract Administrator | Funding source | mSCOA Confiq Code | Ward | Town | Est. Expenditure 2026/2027 | Est. Expenditure 2027/2028 | Est. Expenditure 2028/2029 | Total Estimated Project Cost | Planned Start Date of new contract | Contract period in months (New contract) | Planned Completion Date of new contract | Expected submission date of Specifications (Only on Mondays) | Expected BSC | Expected Date Advertised | Expected Tender Closing Date | Validity Period in days | Expected Date for Technical Evaluation Submission | Expected BEC Date (2 weeks after Technical Evaluation Submission) | Expected BAC Date | Expiry of validty period | Expected Final Award Date | Expected Final Award Date
SECTION A: PROJECTS ON CAPITAL BUDGET FOR 2026/2027 & 2027/2028 & 2028/2029
Technical Captial Projects
Technical |  | Upgrading RSE WTP | Upgrading |  |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/7011/4/0033/2 |  | Riviersonderend | 4317148 | 21343367 | 6519668 | 32180183
Technical |  | Upgrading RSE WTP | Upgrading |  |  |  | Henk Matthee | Nigel Kayser |  | Capital Replacement Reserve | 07/7011/4/0033/3 |  | Riviersonderend |  |  | 4727608 | 4727608
Technical |  | Upgrading Botrivier WWTW, phase 2 | Upgrading | Previous ENG 11/2024/25 |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/6011/7/0090/4 |  | Botriver | 12574418 | 0 | 0 | 12574418
Technical |  | Upgrading Botrivier WWTW, phase 2 | Upgrading | Previous ENG 11/2024/25 |  |  | Henk Matthee | Nigel Kayser |  | Capital Replacement Reserve | 07/6011/7/0090/5 |  | Botriver | 3039897 | 0 | 0 | 3039897
Technical |  | Upgrading Villiersdorp WTP, phase 2 | Upgrading | ENG 05/2025/26 - Cancelled |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/7011/1/0033/0 |  | Villiersdorp | 4610747 | 0 | 0 | 4610747
Technical |  | Upgrading Villiersdorp WTP, phase 2 | Upgrading |  |  |  | Henk Matthee | Nigel Kayser |  | Capital Replacement Reserve | 07/7011/3/0033/0 |  | Villiersdorp |  | 5820594 |  | 5820594
Technical |  | Upgrading Villiersdorp WTP, phase 2 | Upgrading |  |  |  | Henk Matthee | Nigel Kayser |  | Capital Replacement Reserve | 07/7011/3/0033/4 |  | Villiersdorp |  | 4594956 |  | 4594956
Technical |  | Gypsy Queen Water Supply phase 2 | New |  |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/7010/2/0034/2 |  | Grabouw | 1563102 | 0 |  | 1563102
Technical |  | Remedial Works to Damaged Pavilion at the Sportsground in Caledon | Upgrading | ENG 04/2025/26 |  |  | Henk Matthee | Lester Parnell |  |  |  |  | Caledon
Technical |  | Design, Manufacture And Construction Of Structural Steel Portal Frame Structure – Grabouw Taxi Rank. | Upgrading | ENG 06/2025/26 |  |  | Henk Matthee | Lester Parnell |  | Capital Replacement Reserve( Insurance) | 07/4110/2/0055/2 |  | Grabouw | 800000 |  |  | 800000
Technical |  | Design, Manufacture And Construction Of Structural Steel Portal Frame Structure – Grabouw Taxi Rank. | Upgrading | ENG 06/2025/26 |  |  | Henk Matthee | Lester Parnell |  | Capital Replacement Reserve | 07/4110/2/0055/3 |  | Grabouw | 300000 |  |  | 300000
Technical |  | Upgrading Pine View Park Sport ground, Phase 2 | Upgrading | Not Available |  |  | Henk Matthee | Nigel Kayser | Caylin Swarts | MIG, Own | 073115200121 | 13 | Grabouw | 4659000 | 1100000 | 0 | 5759000 | 2027-02-01 | 9 | 2027-10-29 | 2026-07-20 | 2026-07-28 | 2026-08-06 | 2026-09-11 | 90 | 2026-09-25 | 2026-10-12 | 2026-10-16 | 2026-12-10
Technical |  | Bulk sewer provision to erf 313 housing development, Grabouw | New |  |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/6010/2/0009/4 |  | Grabouw | 4784151 |  | 0
Technical |  | Bulk sewer provision to erf 313 housing development, Grabouw | New |  |  |  | Henk Matthee | Nigel Kayser |  | Capital Replacement Reserve | 07/6010/2/0009/5 |  | Grabouw | 1745233 |  |  | 1745233
Technical |  | Grabouw WEST bulk supply upgrades Steenbras upper: NEW 6.5Ml Steenbras upper reservoir & supply lines | New |  |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/7010/2/0034/3 |  | Grabouw | 0 | 1156632 | 11755759 | 12912391
Technical |  | Villiersdorp Destiny Farm Reservoir | New |  |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/7010/3/0034/0 |  | Villiersdorp | 0 | 1156225 | 10241965 | 11398190
Technical |  | Upgrading of the Ultra Fultration Plant in Genadendal | Upgrading |  |  |  | Henk Matthee | Nigel Kayser |  | MIG | 07/7010/5/0034/0 |  | Genadendal | 0 | 1156226 | 3000000 | 4156226
Electrical |  | Electrification TWK Area | Upgrading |  |  |  | Henk Matthee | Zachary Benjamin |  | INEP | 07/7510/0/00020/2 |  | Whole of Municipality | 608696 | 5453044 | 5699131 | 11760871
Electrical |  | Electrification TWK Area | Upgrading |  |  |  | Henk Matthee | Zachary Benjamin |  | Capital Replacement Reserve | 07/7510/0020/3 |  | Whole of Municipality | 91304 | 817956 | 845869 | 1755129
Development
Housing |  | Caledon Riemvasmaak - Phase 1 | New |  |  |  | Namso Baliso | Landile Litholi |  | Capital Replacement Reserve | 07/2111/1/0012/0 |  |  | 305911 |  |  | 305911
Housing |  | Villiersdorp Destiny Farm - Berg en Dal (Phase 1) | New |  |  |  | Namso Baliso | Landile Litholi |  | Capital Replacement Reserve | 07/2111/3/0012/0 |  |  | 1551534 |  |  | 1551534
Housing |  | Botriver Beaumont - Phase 2 - Planning | New |  |  |  | Namso Baliso | Landile Litholi |  | Capital Replacement Reserve | 07/2111/7/0212/0 |  |  | 331213 |  |  | 331213
Housing |  | Greater Grabouw Rooidakke SEF Erf 313 | New |  |  |  | Namso Baliso | Landile Litholi |  | Human Settlements Development Grant In-Kind |  |  | Grabouw | 1200000 |  |  | 1200000
Housing |  | Greyton Erf 595 (538) (Yield reduced) (393) | New |  |  |  | Namso Baliso | Landile Litholi |  | Human Settlements Development Grant In-Kind |  |  | Genadendal/ Greyton | 1000000 | 16000000 | 15400000 | 32400000
Housing |  | Gypsy Queen (500) | New |  |  |  | Namso Baliso | Landile Litholi |  | Human Settlements Development Grant In-Kind |  |  | Grabouw | 1000000 | 20000000 | 16000000 | 37000000
Housing |  | Botrivier Beaumont (1046) IRDP Services (Ph 2 774) | New |  |  |  | Namso Baliso | Landile Litholi |  | Human Settlements Development Grant In-Kind |  |  | Botrivier | 1000000 | 20640000 | 20640000 | 42280000
Housing |  | Greater Grabouw | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Grabouw | 100000 | 5985000 | 5000000 | 11085000
Housing |  | Grabouw Iraq (456) | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Grabouw | 22000000 |  |  | 22000000
Housing |  | Grabouw Hillside (321) (102 + 219) | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Grabouw | 1000000 | 6680000 |  | 7680000
Housing |  | Villiersdorp Destiny Farm (1133) | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Villiersdorp | 50417000 | 16583000 |  | 67000000
Housing |  | Caledon Riemvasmaak (1014) | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Caledon | 11000000 | 16500000 | 15000000 | 42500000
Housing |  | Rooidakke (1054) | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Grabouw | 500000 |  |  | 500000
Housing |  | Riviersonderend Joeslovo Ext | New |  |  |  | Namso Baliso | Landile Litholi |  | Human Settlements Development Grant In-Kind |  |  | Riviersonderend |  | 1500000 |  | 1500000
Housing |  | Botrivier Beaumont (1046) UISP Services Ph1 (272) | New |  |  |  | Namso Baliso | Landile Litholi |  | Informal Settlements Upgrading Partnership Grant In-Kind |  |  | Botrivier |  | 4000000 | 4000000 | 8000000
LED |  | Traders Market and Taxi Rank Upgrade (Planning and Designs) | Upgrading |  |  |  | Namso Baliso | Elana Lotriet |  | RSEP | 07/2116/3/0055/1 |  |  | 700000 |  |  | 700000
|  | Inventory | [11 empty] | 964500 |  |  | 964500
Acting CFO : Financial Services |  | A Riddles | [5 empty] | Director: Technical Services | H Matthee |  |  | GW Hermanus |  | Director: Economic Development and Planning | N Baliso |  | Director: Community Services | W Solomons |  | Manager: IDP |  |  | Name of Acting Accounting Officer/ Delegated Official |  |  | GW Hermanus
Director: Corporate
Signature: | [7 empty] | Signature: | [5 empty] | Signature: |  |  | Signature: |  |  | Signature: |  |  | Signature of Accounting Officer / Delegated Offcial
Date: | [7 empty] | Date: | [5 empty] | Date: |  |  | Date: |  |  | Date: |  |  | Date:

## Operational 2026-27
SCHEDULE OF PROCUREMENT PLANS IN RESPECT OF ADVERTISED COMPETITIVE BIDS FOR THE 2026/2027 FINANCIAL YEAR FOR GOODS, SERVICES AND INFRASTRUCTURE PROJECTS IN EXCESS OF R 300 000 (INCLUDING ALL APPLICABLE TAXES)
Directorate | Project Name / Tender Description | Tender Number | IDP Reference | Strategic Objectives | Contract Owner | Contract Manager | Contract Administrator | Funding source | mSCOA Confiq Code | Ward | Town | Est. Expenditure 2026/2027 | Est. Expenditure 2027/2028 | Est. Expenditure 2028/2029 | Total Estimated Project Cost | Planned Start Date of new contract | Contract period in months (New contract) | Planned Completion Date of new contract | Expected submission date of Specifications (Only on Mondays) | Expected BSC | Expected Date Advertised | Expected Tender Closing Date | Validity Period in days | Expected Date for Technical Evaluation Submission | Expected BEC Date (2 weeks after Technical Evaluation Submission) | Expected BAC Date | Expiry of validty period | Expected Final Award Date | Expected Final Award Date
SECTION A: PROJECTS ON CAPITAL BUDGET FOR 2026/2027 & 2027/2028 & 2028/2029
Technical Captial Projects - Competitive Bidding
Technical | Provision of Services: Taking of Water and Sewerage Samples, Analysing, and Monitoring it in Botrivier, Caledon, Tesselaarsdal, Genadendal, Grabouw, Greyton, Riviersonderend and Villiersdorp for the Period from 01 July 2026 to 30 June 2029 | ENG 01/2026/27 |  |  | Henk Matthee | Ashley Hendricks/Roseline Myburgh |  | Own | 01/6111/0/7541/0 |  | Whole of Municipality | 420385 | 437200 | 454688 |  | 2026-07-01 | 36 | 30/06/2029 |  | 2026-02-17 | 2026-03-16 | 2026-04-07 | 120 | 26/03/2026
[9 empty] | 01/7111/0/7541/0 |  |  | 467129 | 485814 | 505247
Technical | Provision of Recycling Services in Grabouw, Villiersdorp, Caledon, Greyton and Riviersonderend for the Period from Date of Appointment to 30 June 2029 | ENG 02/2026/27 |  |  | Henk Matthee | Jeremy Prins |  | Own | 01/5510/1/7569/0 |  | Whole of Municipality | 945563 | 983386 | 1022721 |  | 2026-07-02 | 36 | 30/06/2029 |  | 2026-03-10 | 2026-03-19 | 2026-04-10 | 120 | 16/04/2026
[9 empty] | 01/5510/2/7569/0 |  |  | 652872 | 678987 | 706146
[9 empty] | 01/5510/3/7569/0 |  |  | 277471 | 288570 | 300113
[9 empty] | 01/5510/4/7569/0 |  |  | 96458 | 100316 | 104329
[9 empty] | 01/5510/5/7569/0 |  |  | 106248 | 110498 | 114918
Electrical | Tender for Labour Cost, Standby and Maintenance in Theewaterskloof Municipal Areas for the Period from 01 July 2026 untill 30 June 2029 |  |  |  | Henk Matthee | Z Benjamin |  | Own |  |  | Whole of Municipality
Electrical | Medium Voltage Switchgear Maintenance and Emergency Repair Work for Theewaterskloof Municipality's Electrical Area of Supply for a Period from Date of Appointment to 30 June 2029 | ELEC 01/2026/27 |  |  | Henk Matthee | Z Benjamin |  | Own | 01/7510/0/7558/0 |  | Whole of Municipality | 350000 | 364000 | 378560 |  | 2026-07-02 | 36 | 30/06/2029 |  | 2026-03-10 | 2026-03-19 | 2026-04-10 | 120
[9 empty] | 01/7510/1/7558/0 |  |  | 300000 | 312000 | 324480
[9 empty] | 01/7510/3/7558/0 |  |  | 250000 | 260000 | 270400
[9 empty] | 01/7510/4/7558/0 |  |  | 300000 | 312000 | 324480
[9 empty] | 01/7510/5/7558/0 |  |  | 300000 | 312000 | 324480
Electrical | Supply and Delivery of Electrical Material - Store Items from Date of Appointment to 30 June 2029 | ELEC 02/2026/27 |  |  | Henk Matthee | Z Benjamin |  | Own | 01/7510/4/9025/3 |  | Whole of Municipality | 5850 | 6084 | 6327 |  | 2026-07-03 | 36 | 30/06/2030 |  | 2026-03-10 | 2026-03-20 | 2026-04-10 | 120
[9 empty] | 01/7510/3/9025/0 |  |  | 15000 | 15600 | 16224
[9 empty] | 01/7510/1/9025/2 |  |  | 50000 | 52000 | 54080
[9 empty] | 01/7510/3/9025/1 |  |  | 243400 | 253136 | 263261
[9 empty] | 01/7511/3/9025/0 |  |  | 75120 | 78125 | 81250
[9 empty] | 01/7511/4/9025/0 |  |  | 36702 | 38170 | 39697
[9 empty] | 01/7511/5/9025/0 |  |  | 94728 | 98517 | 102458
Electrical-Formal Written Quotations (TWK 2)
Electrical | Monitoring of Voltage Quality Recorders on Five (5) Existing Vectographs/Vecto 111 for the Period from 1 July 2026 to 31 June 2027 |  |  |  | Henk Matthee | M Theunissen |  | Own | 01/7510/0/7558/0 |  | Whole of Municipality | 350000
Development - Competitive Process
Property Development | The Sale of Erf 911 Riviersonderend for Business Purposes | TPM 05/2025/26 |  |  |  | Edward Wessels |  | Income | [12 empty] | 2026-03-04 | 2026-04-10 | 120
Community - Competitive Bidding
Community | Supply and Delivery of Construction Materials from Date of Appointment to 30 June 2028 | COMM 08/2025/26 |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Supply and Delivery of Black Bags for the Period from Appointment Date to 30 june 2028 |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Supply and Delivery of Building Material for the Period from Date of Appointment to 30 June 2029 |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Supply and Delivery of Pipes and Fittings from Date of Appointment to 30 June 2029 |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Maintenance and Repairs of Water and Wastewater Infrastructure Equipment for a Period from Date of Appointment to 30 June 2029 |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Supply and delivery of PPE from date of a appointment to 30 June 2029 |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Supply and Delivery of yellow plant from date of a appointment to 30 June 2029 |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Supply and Delivery of Wheelie Bins |  |  |  | Jan Barnard |  |  | Own | 01/5510/1/9025/2 |  | Caledon | 100000 | 104000 | 108160
Community |  |  |  |  | Jan Barnard |  |  | Own | 01/5510/2/9025/2 |  | Grabouw | 300000 | 312000 | 324480
Community |  |  |  |  | Jan Barnard |  |  | Own | 01/5510/3/9025/2 |  | Villiersdorp | 105000 | 109200 | 113568
Public Safety | Supply, Implementation and Management of a Computerized Traffic Contravention Management System (TCMSC) with Call Centre Module for the Processing of Traffic – and Law Enforcement Offences and the Provision of Operational Support and Maintenance from the Date of Appointment |  |  |  | Jan Barnard |  |  | Revenue | Various votes |  | Whole of Municipality | Various amounts
Public Safety | The Provision of Security Services for Theewaterskloof Municipality: Guarding, Alarm Installation, Monitoring and Response from Date of Appointment |  |  |  | Jan Barnard |  |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community -Formal Written Quotations (TWK 2)
Community | Cutting of grass in Riviersonderend for a period from date of appointmnet until 30 June 2027 |  |  |  | Jan Barnard | A Wessels |  | Own | 01/3117/4/7020/0 |  | Whole of Municipality | 51750 | 53820 | 55973
Community | Cleaning and Clearing of Villiersdorp Cemeteries on a Quarterly Basis From 01 July 2026 untill 30 June 2027 |  |  |  | Jan Barnard | JC Mong |  | Own | 01/3121/3/7571/0 |  | Whole of Municipality | 280000 | 291200 | 302848
Community | Cleaning of Streets, Around Toilets Illegal Dumping Areas in Informal/Formal Areas Including Waterways From 01 July 2026 until 30 June 2027 on a Weekly Basis in Villiersdorp |  |  |  | Jan Barnard | JC Mong |  | Own | Various votes |  | Whole of Municipality | Various amounts
Community | Cutting of Grass and Cleaning the Areas at Various Locations in Villiersdorp on a Monthly Basis from 01 July 2026 to 30 June 2027 |  |  |  | Jan Barnard | JC Mong |  | Own | 01/3117/1/7020/0 |  | Whole of Municipality | 50000 | 52000 | 54080
Public Safety | Hosting of Repeater Equipment - Monthly Rental, IP Connectivity Between Sites - Monthly Rental, DMR Radio Equipment Maintenance Requirement for Theewaterskloof Municipality Department Public Safety from 01 July 2025 to 30 June 2026 |  |  |  | WS Johannes | R Hendricks |  | Own | 01/3125/1/9660/0 |  | Whole of Municipality | 50000 | 52000 | 54080
Corporate - Competitive Bidding
ICT | The Appointment of Fibre Internet Service Provider for all Theewaterskloof Municipal Sites, as and when required from 01 July 2026 untill 30 June 2029 |  |  |  | GW Hermanus | Maphefa Joel Rasekgala |  | Own | 01/1115/9/9572/4 |  | Whole of Municipality | 1400000 | 1456000 | 1514240
ICT | Hosting andMmaintenance of Theewaterskloof Munisipality's Website from 01 July 2026 until 30 June 2029 |  |  |  | GW Hermanus | Maphefa Joel Rasekgala |  | Own | 01/1115/9/9569/9 |  | Whole of Municipality | 120000 | 124080 | 128051
ICT | Licensing Fees of all Windows, Anti Virus, ect. needs |  |  |  | GW Hermanus | Maphefa Joel Rasekgala |  | Own | 01/3125/0/9569/0 01/1115/9/9570/9 |  | Whole of Municipality | 70,000 4,000,000 | 72,800 4,160000 | 75712 4326400
Corporate Services | Appointment of a service provider to provide training from the date of appointment until 30 June 2028 | COR 05/2025/26 |  |  | GW Hermanus | L Sheane |  | Own | Various votes |  | Whole of Municipality | Various amounts
Corporate Services | Group life insurance for the period from 1 July 2026 to 30 June 2029 | COR 02/2026/27 |  |  | GW Hermanus | Charles Fisher |  | Own | Various votes |  | Whole of Municipality | Various amounts | [7 empty] | 2026-04-28 | 2026-05-08 | 2026-06-12 | 120
Corporate - Formal Written Quotations (TWK 2)
Corporate Services | Translation of Documents from Afrikaans to English and Vise Versa for Theewaterskloof Municipality for the Period from 01 July 2026 to 30 June 2027 | KOR 01/2026/27 |  |  | GW Hermanus | Marilize Faul |  | Own | 01/1112/0/7043/1 |  | Whole of Municipality | 10000 | 10400 | 10816
Corporate Services | "APPOINTMENT OF A PANEL OF SERVICE PROVIDERS TO SUPPLY AND DELIVER STOCK TO THE HEAD OFFICE OF THEEWATERSKLOOF MUNICIPALITY FOR THE PERIOD 01 JULY 2026 TO 30 JUNE 2027" | KOR 03/2026/27 |  |  | GW Hermanus | Marilize Faul |  | Own | 01/1110/9/9010/1 |  | Whole of Municipality | 100000 | 104000 | 1081260
Corporate Services | Appointment of a Panel of Service Providers to Supply and Deliver Stationary for the Directorate Corporate Services at the Head Office of Theewaterskloof Municipality for the Period 01 July 2026 till 30 June 2027 | KOR 02/2026/27 |  |  | GW Hermanus | Marilize Faul |  | Own | 01/1110/9/9010/5 |  | Whole of Municipality | 300000 | 312000 | 324480
Corporate Services | Conclusion of Maintenance Agreements for Forty (40) Bizhub Photocopiers in Various Offices of Theewaterskloof Municipality for the Period 01 July 2026 to 30 June 2027 |  |  |  | GW Hermanus | Marilize Faul |  | Own | 01/1110/9/7572/1 |  | Whole of Municipality | 192581 | 200284 | 208295
Finance - Competitive Bidding
Finance | Prepaid Electricity | FIN 01/2026/27 |  |  | A Riddles | J Van Niekerk |  | Own | 01/1510/9/7504/4 |  | Whole of Municipality | 1400000 | 1456000 | 1514240
Finance | Bill Payments | FIN 02/2026/27 |  |  | A Riddles | J Van Niekerk |  | Own | 01/1510/9/7504/7 |  | Whole of Municipality | 1200000 | 1248000 | 1297290
Finance | Complete Infrastructure Asset Verification from 01 July 2026 to 30 June 2029 | FIN 03/2026/27 |  |  | A Riddles | J Colyn |  | Own | 01/1520/9/9571/0 |  | Whole of Municipality | 1500000
Finance - Formal Written Quotation (TWK 2)
Finance | Vetting System (Suppliers / consumers) | FI 01/2026/27 |  |  | A Riddles | J Van Niekerk |  | Own | 01/1510/9/7504/8 |  | Whole of Municipality | 221242 | 230092 | 239296
Finance | Debt Collection |  |  |  | A Riddles | J Van Niekerk |  | Own | 01/1510/9/7505/2 |  | Whole of Municipality | 300000 | 312000 | 324480
Acting CFO : Financial Services | A Riddles |  |  |  |  | Director: Technical Services | H Matthee |  |  | GW Hermanus |  | Director: Economic Development and Planning | N Baliso |  | Director: Community Services | W Solomons |  | Manager: IDP |  |  | Name of Acting Accounting Officer/ Delegated Official |  |  | GW Hermanus
Director: Corporate
Signature: | [5 empty] | Signature: | [5 empty] | Signature: |  |  | Signature: |  |  | Signature: |  |  | Signature of Accounting Officer / Delegated Offcial
Date: | [5 empty] | Date: | [5 empty] | Date: |  |  | Date: |  |  | Date: |  |  | Date: